## 日本語
# | Title | 依頼・確認内容 Details of request / confirmation item | 補足 Supplement | 起票者 Raised by | 起票日付 Raised Date | ステータス Status | 回答内容 Contents of Answer / Progress status | 備考 / Remark
Draft 1 | MID Server 新規構築・一元管理 | 利用部門または各社が MID Server を個別に構築する場合、新規構築の管理、重複構築の防止、および台数・用途・管理責任者の一元把握について、HDS のご経験に基づく推奨方法をご教示ください。 | 想定リスク：ユーザー側での個別構築により、 MID Server が無秩序に増加する可能性があります。 1. 申請・構築の必要性確認・台帳登録に適した プロセスをご教示ください。 2. 既存の MID Server の共用と新規構築を判断する 基準をご教示ください。 3. 用途・対応範囲・管理責任者を一元管理し、 実際の構築状況と定期的に照合する方法をご教示ください。 利用可能な標準機能、別途定めるべき運用ルール、 および既存プロジェクトの事例をご紹介ください。 |  |  | ドラフト 内部確認待ち |  | 元の課題 #14：MID Server が無秩序に増加するリスクに対応。 関連する既存 QA：#11「Mid Server」（オフィスの共用と配置範囲）。 本項目では、新規構築および台帳登録の管理方法を補足確認します。
Draft 2 | MID Server バージョン・ アップグレード管理 | ユーザー側ごとの更新時期のばらつき、長期間の未更新、アップグレード失敗の放置を防ぐため、本プロジェクトに適した MID Server のバージョン・アップグレード管理方法をご教示ください。 | 想定リスク：個別の保守によりバージョン差異が生じ、 アップグレード結果の把握が遅れる可能性があります。 1. 目標バージョンとアップグレード計画の決め方、 および許容できるバージョン差異をご教示ください。 2. 現行バージョン・実施結果・未更新や失敗した対象を 一元的に確認する方法をご教示ください。 3. 実施調整・完了確認・失敗時の対応について、 中央管理チームとユーザー側の推奨分担をご教示ください。 推奨プロセス、利用可能な標準機能、 および運用上の注意点をご教示ください。 |  |  | ドラフト 内部確認待ち |  | 元の課題 #14：MID Server 間でバージョンが不揃いになるリスクに対応。 関連する既存 QA：#12「Mid Server」（運用責任の分担）。 本項目では、バージョンの可視化とアップグレード実施管理を補足確認します。全台同時のアップグレードを前提とするものではありません。
Draft 3 | MID Server 日常運用・廃止管理 | 既存の運用責任分担に関する議論を踏まえ、構築後に管理されない MID Server が発生しないよう、継続的な保守、管理責任者の引継ぎ、および停止・廃止の管理方法をご教示ください。 | 想定リスク：責任者が不明確な場合や担当者の変更時に、 障害が放置されたり、未使用の MID Server が 残り続けたりする可能性があります。 1. 稼働状況の確認・アラート受領・障害対応の 推奨分担をご教示ください。 2. 責任者情報を維持し、人員・組織変更時の引継ぎを 確実に行う方法をご教示ください。 3. 長期停止中・未使用・用途がなくなった MID Server を 定期的に把握する方法と、停止・廃止前の確認事項を ご教示ください。 HDS の運用プロセスや管理台帳の事例をご紹介ください。 |  |  | ドラフト 内部確認待ち |  | 元の課題 #14：保守されない MID Server が増加するリスクに対応。 関連する既存 QA：#12「Mid Server」（運用責任の分担）。 本項目では、継続的な保守、担当者の引継ぎ、および廃止プロセスを補足確認します。
Draft 4 | MID Server 配置・クラスター／ 冗長構成 | 既存の「MID Server Workload Distribution」QA の回答を踏まえ、本プロジェクトに適した配置およびクラスター／冗長構成について、推奨理由、適用条件、制約とあわせてご教示ください。 | 1. 集約配置と会社・ネットワーク範囲・用途別の配置を 判断する主な基準をご教示ください。 2. 障害時・計画メンテナンス時の切替や処理継続について、 自動化できる操作、手動操作が必要な箇所、 および復旧後の確認事項をご教示ください。 3. Discovery と ACC に同じクラスター・切替方式を 適用できるとは限らないため、それぞれの推奨方法を 分けてご説明ください。 本プロジェクトに参考となる構成例や運用事例を ご紹介ください。 |  |  | ドラフト 内部確認待ち |  | 会議で追加された確認事項。 関連する既存 QA：#12「MID Server Workload Distribution」 既存の回答を踏まえ、本プロジェクトへの適用方法を確認します。 ACC 向け MID Server は、大きめの構成で台数を抑える方向が議論されています。具体的なサイジングと台数は、HDS の担当メンバーから別途共有いただく結果待ちであり、本項目では結論を前提としません。

## English
# | Title | 依頼・確認内容 Details of request / confirmation item | 補足 Supplement | 起票者 Raised by | 起票日付 Raised Date | ステータス Status | 回答内容 Contents of Answer / Progress status | 備考 / Remark
Draft 1 | MID Server Provisioning and Central Inventory | If individual user departments or companies provision their own MID Servers, please advise on recommended practices for governing new deployments, preventing duplication, and maintaining a central inventory of their numbers, purposes and owners, based on HDS's project experience. | Potential risk: Independent provisioning by user teams could lead to uncontrolled growth in MID Server deployments. 1. What process is recommended for requests, assessment of the need for a new deployment, and inventory registration? 2. What criteria should determine whether to share an existing MID Server or deploy a new one? 3. How should purpose, coverage and ownership be recorded centrally and checked periodically against actual deployments? Please distinguish available out-of-the-box features from operating procedures that need to be established, and share relevant project examples. |  |  | Draft Pending internal review |  | Addresses original issue #14: the risk of uncontrolled MID Server growth. Related existing QA: #11, 'Mid Server' (shared office locations and deployment boundaries). This item supplements the existing QA with provisioning governance and inventory registration.
Draft 2 | MID Server Version and Upgrade Management | Please recommend an approach to MID Server version and upgrade management for this project, to address differing update schedules across user teams, prolonged delays in updating, and upgrade failures left unresolved. | Potential risk: Decentralized maintenance could create version differences and delay visibility of upgrade results. 1. How should target versions and upgrade plans be determined? Which version differences, if any, are acceptable? 2. How can current versions, upgrade results, outstanding updates and failures be monitored centrally? 3. How should the central management team and user teams divide responsibility for upgrade coordination, completion checks and failure handling? Please advise on recommended processes, available out-of-the-box features and operational considerations. |  |  | Draft Pending internal review |  | Addresses original issue #14: the risk of inconsistent MID Server versions. Related existing QA: #12, 'Mid Server' (operational responsibilities). This item adds version visibility and upgrade execution management. It does not assume that all MID Servers must be upgraded simultaneously.
Draft 3 | MID Server Operations, Ownership and Decommissioning | Building on the existing discussion of operational responsibilities, please recommend ongoing maintenance, ownership handover, and shutdown and decommissioning practices to prevent MID Servers from being left unmanaged after deployment. | Potential risk: Unclear ownership or staff changes could leave incidents unresolved and unused MID Servers in place. 1. How should responsibilities for health checks, alert handling and incident response be assigned? 2. How should ownership records be maintained and handover ensured when personnel or organizational structures change? 3. How should long-stopped, unused or no-longer-required MID Servers be identified periodically? What checks are needed before shutdown or decommissioning? Please share examples of HDS's operating procedures and management registers. |  |  | Draft Pending internal review |  | Addresses original issue #14: the risk of increasing numbers of unmaintained MID Servers. Related existing QA: #12, 'Mid Server' (operational responsibilities). This item adds ongoing maintenance, ownership handover and decommissioning processes.
Draft 4 | MID Server Deployment, Clustering and Redundancy | Following the response to the existing 'MID Server Workload Distribution' QA, please recommend a deployment and clustering or redundancy approach suitable for this project, including the rationale, applicability and limitations. | 1. Should deployment be centralized or separated by company, network scope or purpose? What are the main decision criteria? 2. How should failover or continued processing be handled during failures and planned maintenance? Which actions can be automated, which require manual intervention, and what should be checked after recovery? 3. Please distinguish the recommended approaches for Discovery and ACC, without assuming that the same clustering or failover mechanism applies to both. Please share relevant reference architectures and operational examples for this project. |  |  | Draft Pending internal review |  | Additional topic raised in the meeting. Related existing QA: #12, 'MID Server Workload Distribution'. This item follows up on the existing response to confirm how it applies to this project. For MID Servers supporting ACC, the direction under discussion is fewer, larger servers. Specific sizing and server counts are awaiting separate feedback from the responsible HDS team member. No final sizing or count is assumed here.